## Action Log
ACTION LOG
PROJECT NAME: PMI CONFERENCE |  |  | PROJECT MANAGER: ANUOLUWAPO BELLO |  |  |  |  | DATE: 01/02/2024
ID | Action | Owner | Status | Target Completion Date | Progress | Source | Date Created | Comments | Priority
1 | Develop Project Charter | ANUOLUWAPO BELLO | In Progress | February 10, 2024 | 20% | Course Project Overview | January 31, 2024 | Fill in details from project overview and experience. | High
2 | Identify and contact potential volunteers | VICTORIA | Not Started | February 15, 2024 | 0% | Stakeholder Management Section | January 31, 2024 | Need at least 8 volunteers for various roles. | High
3 | Secure meeting space and catering for project kickoff | QUEEN ESTHER | Not Started | February 20, 2024 | 0% | Schedule Management Section | January 31, 2024 | Consider budget and location for kickoff meeting. | Medium
4 | Develop preliminary website development plan | CHRISTIANA | Not Started | March 1, 2024 | 0% | Resource / Procurement Management Section | January 31, 2024 | Outline website functionalities and milestones. | High
5 | Begin risk identification and analysis | MERCY | Not Started | March 5, 2024 | 0% | Risk Management Section | January 31, 2024 | Identify potential risks like COVID, inflation, and labor shortages. | Medium

## Template Help
Overview / grading requirements:
A project action log is simply a single place for your team's To Do list. It consolidates all the actions from meeting minutes, phone calls, etc.
The purpose of an action log is to consolidate actions into one place to save time when you're tracking and monitoring progress.
It is not the same as the project schedule and should not overlap with the project schedule or action plan.
The benefits of an action log are: keeping all actions together in one consolidated location, making it easy to see who is doing what, making it easy to see the status of open actions, and improving communication in the team.
Helpful Links:
https://www.liquidplanner.com/blog/ask-a-pm-a-guide-to-action-log-tasks-and-activities/
https://www.youtube.com/watch?v=ep4otYAXqjs
Example: