## Log
ASSUMPTION LOG
St. LOUIS PMI CONFERENCE
PROJECT MANAGER: ANUOLUWAPO BELLO |  |  |  |  | DATE: 31/01/2024
ID | Category | Assumption | Responsibility | Due Date | Status | Actions
A01 | Venue | The hotel is open and functioning normally without any closures due to renovations, management changes, or external factors like natural disasters or public health emergencies. | Queen Esther | 2024-01-09 | Open | Logistic team to meet with Hotel manager to confirm venue availability and secure contract within the first month of the project.
A02 | Sponsorship | There is an agreement that a certain number of businesses (ten) will contribute prizes for a conference. | Robinson | 2024-01-04 | Open | Marketing team is currently Developing sponsorship packages and secure agreements with business sponsors.
A03 | Registration | There is a sufficient demand for the event or service being offered, implying that there is a customer base willing to pay the registration fee of $1,500. | Anuoluwapo Blessing Bello | 05/31/24 | Open | Project manager will meet with marketing team to monitor registration process and ensure all attendees have paid in full by the end of the month.
A04 | Presenters | PMI board is assumed to be in charge of identifying, inviting, and confirming the participation of all presenters for the event. | Anuoluwapo Blessing Bello | 06/30/24 | Open | Project manager will coordinate with PMI International to confirm presenter lineup and fees.
A05 | Website | The event website will be developed by PMI International board for a flat rate of $5,000. | Christiana | 04/30/24 | Open | PMI board will meet with web developer to manage website development through analysis, design, development, and implementation phases.
A06 | Catering | Aramark will be responsible for providing two meals a day, specifically breakfast and lunch with a cost of $12,000 per day. | Queen Esther | 2024-01-06 | Open | Logistics team to meet with Aramark to finalize catering contract and ensure all logistics are in place for the event.
A07 | Audio/Visual | Swank Audio/Video Production Company will cover all A/V needs with a cost of $10,000 per day. | Christiana | 2024-01-06 | Open | Technology team will meet with Swank Audio Company to secure the contract and coordinate A/V requirements for the conference.
A08 | Workshops | PMI volunteers will create workshop content and all planning will be completed by end of May. | Agnes Dell | 05/31/24 | Open | Program Lead will meet with PMI volunteers to plan major deliverables and milestones for workshop development and ensure materials are sent to printer.
A09 | Survey | It is assumed that the survey will be developed quickly to ensure it is ready in time for the event's conclusion. | Anuoluwapo Blessing Bello | 06/25/24 | Open | Project manager will develop and implement the event survey, and prepare to summarize data post-event.
A10 | Volunteer Support | At least 50 local PMI Chapter members will volunteer for registration and coordination. | Victoria | 2024-01-06 | Open | Volunteer Coordinator will recruit and train volunteers, ensuring they are added to the attendee count for budgeting.

## Template Help
Overview / grading requirements:
An assumption log is a document that a project manager utilizes to capture, record, and track assumptions on a project throughout its life cycle. It is the list of all assumptions identified as affecting the project. (may include constraints)
An assumption log is simply a place to log all assumptions and track the validation of each one. We make project assumptions out of necessity.
The assumption log should contain the following items for each assumption: The date the assumption was first logged. A category for the assumption, e.g. budget, scheduling, product. A name and description for the assumption.
Helpful Links:
https://www.projectmanagementdocs.com/template/project-documents/assumption-log/
https://www.youtube.com/watch?v=C9hifA0M7r8
Example: