## Comm Plan
PROJECT COMMUNICATION PLAN TEMPLATE
PROJECT NAME: PMI CONFERENCE |  | PROJECT MANAGER: ANUOLUWAPO B BELLO |  | START DATE: JANUARY, 2024 |  | COMPLETION DATE: JUNE, 2024
Meeting Name | Purpose | Owner | Method | Audience | Frequency | Status
Kickoff Meeting | Introduce the project to stakeholders, manage expectations and set expectations | ANUOLUWAPO B BELLO | In-person meeting | Project team, key stakeholders, PMI Chapter Board | Once | 1/14/22 - Meeting held and kickoff approved
Weekly Status Calls | To review progress, address any RAID (Risks, Assumptions, Issues, Dependencies) log items, and make necessary adjustments to the project plan. | ANUOLUWAPO B BELLO | Virtual (MS Teams) | PMI Chapter Board, project team | Weekly | Ongoing throughout the project
Daily Updates During Event | To provide quick, daily summaries of the event's progress, highlight any immediate concerns, and prepare for the next day. | QUEEN ESTHER | Email/MS Teams | Project sponsor, project team | Daily during the event week | Planned for the event week
Event Name | Purpose | Owner | Method | Audience | Frequency | Status
PMI Conference | To facilitate networking among PMI members, provide learning opportunities for earning PDUs, and showcase project management and agile project management tracks. | ANUOLUWAPO B BELLO | On-site | PMI members, volunteers, business sponsors | Quarterly, specific to St. Louis in the summer | Scheduled for the first full week in June
Workshop | To provide in-depth learning experiences on creating a project charter and using personal Kanban. | EVELYN | On-site | Conference attendees | Once | Planning phase, with major deliverables and milestones outlined
Report Name | Purpose | Owner | Method | Audience | Frequency | Status
Event Survey Report | To gather feedback from attendees on the event's success and areas for improvement. | ROBINSON | Online survey | PMI Chapter Board, project team | Once after the event | Survey to be developed ASAP, report to be sent out after the event

## Template Help
Overview / grading requirements:
A project communication plan/matrix is an agreement between collaborators and stakeholders that outlines what, when, and how information will be shared at key intervals.
Information like status updates, task-related questions, and meeting details should all be included in this written guide.
Every good communication management plan should answer the 5 Ws: who, what, when, where, and why.
Helpful Links:
https://www.lucidchart.com/blog/project-management-communication-plan
https://www.teamgantt.com/blog/project-management-communication-plan
Example: