## Log
St. LOUIS PMI CONFERENCE
DECISION LOG
Project Name: Anuoluwapo B Bello |  |  | Project Sponsor: Pam Meister
No. | Decision | Impact | Proposed Date | Proposed By | Status | Approved By | Date | Resulting Action/Comments
1 | The decision to confirm the venue for the PMI St. Louis Conference 2024 by 09/01/2024 is made to ensure the availability of the desired location, start planning logistics, and avoid scheduling conflicts. | High | 2024-01-09 | Project Team | Approved | Pam Meister | 01/25/2024 | Approved. Action item assigned to project manager
2 | The decision to confirm the speaker lineup for the PMI St. Louis Conference 2024 by 06/01/2024 is made to finalize the list of presenters well in advance, allowing ample time for promotion and marketing efforts. | Medium | 2024-01-06 | Project Team | Pending | Pam Meister | 01/25/2024 | Awaiting approval
3 | The decision to launch the marketing and sponsorships campaign for the PMI St. Louis Conference 2024 by 04/01/2024 is made to attract sponsors and build attendee interest with ample lead time. | High | 2024-01-04 | Robinson | Approved | Pam Meister | 01/25/2024 | Approved as no material impact
4 | Web developer team have made the decision to launch the new website and registration system on the scheduled date. The website will feature an intuitive design, streamlined navigation, and a simplified registration process to ensure a positive user experience. | High | 2024-01-03 | Christiana | Pending | Pam Meister | 01/25/2024 | Awaiting approval
5 | The decision has been made to finalize the schedules and materials for the upcoming training works | Medium | 2024-01-02 | Agnes Dell | Approved | Pam Meister | 01/25/2024 | Approved. Action item assigned to Program lead
6 | The decision to close attendee registration for the St. Louis PMI Conference 2024 on scheduled date was made to ensure that the event can be managed effectively, with a finalized list of participants. | Medium | 2025-12-01 | Project Team | Approved | Pam Meister | 01/25/2024 | Approved as no material impact
7 | After thorough evaluation and comparison of potential vendors, the Logistic team has decided to confirm Aramark as the final choice for Catering for the upcoming event | High | 2025-01-01 | Logistics Lead | Pending | Pam Meister | 01/25/2024 | Awaiting approval
9 | Implement a structured approach for distributing post-event surveys to collect attendee feedback for the purpose of improving future events. | Low | 2025-09-03 | Project Team | Pending | Pam Meister | 01/25/2024 | Awaiting approval
10 | Decision to approve the Final Financial Report and Evaluation Completion. | High | 03/25/2025 | Sandra | Pending | Pam Meister | 01/25/2024 | Awaiting approval

## Template Help
Overview / grading requirements:
A decision log is a beneficial communication tool to apprise stakeholders regarding how a decision was reached, options considered, and who approved the decision.
It may eliminate potential confusion and prevent project teams from unnecessary decision "churning".
To write a decision log, explain the choice the team made and the reasons for making it. If you considered other alternatives, list them and explain why you ruled them out.
Helpful Links:
https://rebelsguidetopm.com/project-decision-log/
Example: