## Log
DEPENDENCY LOG
PROJECT NAME: PMI CONFERENCE
PROJECT MANAGER: ANUOLUWAPO BELLO
PROJECT SPONSOR: PAM MEISTER
ID | Date | Owner |  | Importance | Status | Comments
1 | 2024-02-01 | Queen Esther | budget are dependent on Venue Confirmation | High | Approved | Logistic team will confirm venue 9-12 months before the conference to ensure availability and budget alignment.
2 | 2024-02-01 | Agnes Dell | Selection of speakers are dependent of the conference theme | High | Pending | Awaiting approval of conference theme before the conference to align with the theme and secure preferred dates.
3 | 2024-02-01 | Robinson | Marketing and Sponsorships Campaign are dependent on strategic planning and execution | High | Pending | Awaiting approval date to begin campaign before the conference to maximize exposure and sponsorship opportunities.
4 | 2024-02-15 | Christiana | Website and Registration System depends on the server | High | Pending | Awaiting approva to launch website before the conference to allow ample time for attendees to register and for testing system reliability.
5 | 2024-02-29 | Agnes Dell | Workshop Schedules are dependent on availability of speakers | High | Pending | Awaiting approval to finalize the availability of speakers 2-3 months before the conference to accommodate speaker schedules and session planning.
7 | 2024-03-28 | Queen Esther | Logistics and Vendor Confirmation are dependent on contract finalization | High | Approved | Logistic team has finalized contract with logistics and vendors before the conference to ensure all services are secured and coordinated.
9 | 2024-08-12 | Robinson | Post-Event Surveys are dependent on distribution method like emails or social media | Medium | Approved | Marketing team will distribute surveys via emails within 1-2 weeks after the conference to capture timely and relevant attendee feedback

## Template Help
Overview / grading requirements:
The dependencies log will capture at least who the project is dependent upon and what they should deliver and when.
It is possible for a project to have interdependencies. This is where tasks, milestones, etc within the same project are dependent on each other.
In order to identify project dependencies, look for tasks that the team cannot perform until they receive information or deliverables from a previous task. Those tasks are dependent. Think of your whole project as a series of workflows or a flowchart.
Helpful Links:
Example: