## Log
ISSUE MANAGEMENT LOG
PROJECT NAME: PMI CONFERENCE
PROJECT SPONSOR: PAM MEISTER
PROJECT MANAGER NAME: ANUOLUWAPO B BELLO
ID | Priority | Status | Severity | Category | Description | Owner | Responsible | Due Date | Completion Date | Comments
1 | High | Open | Critical | Website Development | Website not migrated from PMI International website | CHRISTIANA | Content Developer: Evelyn | 2024-01-31 | 2024-02-29 | Design phase started
2 | Medium | In Progress | Major | Vendor Contracts | Contract with Drury Hotel not finalized | ANUOLUWAPO BELLO | Procurement Team: Queen Esther | 2024-02-15 |  | Negotiations ongoing
3 | High | Open | High | Presentations | Speaker confirmations not received for Agile track | AGNES DELL | Content Developer: Evelyn | 2024-02-20 |  | Outreach efforts underway
4 | Low | Open | Minor | Registration | Online registration form not yet functional | ANUOLUWAPO BELLO | Web Developer: Christiana | 2024-02-23 |  | Integration with website in progress
5 | Medium | Open | Moderate | Budget | Potential cost overrun due to inflation | ANUOLUWAPO BELLO | Finance Team: Sandra | 2024-03-01 |  | Monitoring market trends and adjusting budget as needed

## Template Help
Overview / grading requirements:
The issue log, sometimes also known as an issue register, is a project document where all issues that are negatively affecting the project are recorded and tracked.
When an issue log is created, it provides a tool for reporting and communicating all that is happening within the project.
An issue log is a simple list or spreadsheet that helps managers track the issues that arise in a project and prioritize a response to them.
Having an issue log is important because it ensures team members properly document any challenges they may face during a project's life cycle.
Helpful Links:
https://pmstudycircle.com/issue-log/
https://www.youtube.com/watch?v=kQMaJ5GA7r4
Example: