## Schedule
PROJECT SCHEDULE
PROJECT MANAGER: ANUOLUWAPO BELLO |  |  |  | PROJECT SPONSOR: PAM MEISTER
ID | Progress % | Task Description | Resource Name | Start Date | Planned End Date | Duration Estimate | Work Estimate | Predecessor Task ID
1 | 100% | Project Initiation | Anuoluwapo Blessing Bello | 2024-01-01 | 2024-07-01 | 1 week | 40 hours
1.1 | 80% | Develop Project Charter | Anuoluwapo Blessing Bello | 2024-12-01 | 01/14/2024 | 2 days | 16 hours
1.2 | 75% | Stakeholder Identification | Anuoluwapo Blessing Bello | 01/19/2024 | 01/20/2024 | 1 day | 8 hours | 1.1
1.3 | 0% | Project Kick-off Meeting | Anuoluwapo Blessing Bello | 01/30/2024 | 01/30/2024 | 1 day | 4 hours | 1.2
2 | 50% | Planning | Project Team | 2024-01-02 | 2024-01-03 | 1 month | 160 hours | 1
2.1 | 75% | Develop Work Breakdown Structure (WBS) | Anuoluwapo Blessing Bello | 2024-01-02 | 2024-07-02 | 1 week | 40 hours | 1.3
2.2 | 0% | Risk Management Planning | Mercy | 2024-08-02 | 02/14/2024 | 1 week | 40 hours | 2.1
2.3 | 60% | Budget Estimation | Sandra | 02/15/2024 | 02/21/2024 | 1 week | 40 hours | 2.2
2.4 | 0% | Schedule Development | Anuoluwapo Blessing Bello | 02/22/2024 | 02/28/2024 | 1 week | 40 hours | 2.3
3 | 0% | Execution | Project Team | 2024-01-03 | 2024-01-05 | 2 months | 320 hours | 2
3.1 | 45% | Website and Registration System Launch | Christiana | 2024-01-03 | 03/15/2024 | 2 weeks | 80 hours | 2.4
3.2 | 65% | Marketing and Sponsorships Campaign Launch | Robinson | 03/16/2024 | 2024-01-04 | 2 weeks | 80 hours | 3.1
3.3 | 75% | Venue Confirmation | Queen Esther | 2024-02-03 | 2024-09-03 | 1 week | 40 hours | 2.4
3.4 | 35% | Speaker Lineup Confirmed | Agnes Dell | 2024-10-03 | 03/24/2024 | 2 weeks | 80 hours | 3.3
3.5 | 30% | Workshop Schedules and Materials Finalized | Agnes Dell | 03/25/2024 | 2024-08-04 | 2 weeks | 80 hours | 3.4
4 | 35% | Monitoring and Controlling of project | Anuoluwapo Blessing Bello | 2024-01-03 | 2024-01-06 | 3 months | 240 hours | 3
4.1 | 20% | Performance Reporting | Sandra | 2024-01-03 | 2024-01-06 | 3 months | 120 hours | 3
4.2 | 30% | Risk Monitoring | Mercy | 2024-01-03 | 2024-01-06 | 3 months | 120 hours | 3
5 | 0% | Closing | Anuoluwapo Blessing Bello | 2024-01-06 | 06/26/2024 | 3.5 weeks | 140 hours | 4
5.1 | 0% | Attendee Registration Closes | Christiana | 2024-12-07 | 07/13/2024 | 1 day | 8 hours | 3.5
5.2 | 0% | Final Logistics and Vendor Confirmation | Queen Esther | 07/17/2024 | 07/18/2024 | 1 day | 8 hours | 5.1
5.3 | 0% | Conference Opening Ceremony | Anuoluwapo Blessing Bello | 07/20/2024 | 07/21/2024 | 1 day | 8 hours | 5.2
5.4 | 0% | Post-Event Surveys Distributed | Robinson | 2024-01-08 | 2024-02-08 | 1 day | 8 hours | 5.3
5.5 | 0% | Final Financial Report and Evaluation | Sandra | 2024-12-08 | 03/13/2024 | 1 day | 8 hours | 5.4
5.1
5.2
5.3
5.4
5.5
5.6

## Example
Project Schedule Template
ID | Progress % | Task Description | Resource Name | Start Date | Planned End Date | Duration Estimate | Work Estimate | Predecessor Task ID | Notes:
1 |  | Project Management Activities | [6 empty] | << Summary task
1.1 | 100% | Complete Project Charter | PM, Team | 2021-05-24 | 2021-06-06 | 1 day | 4 hours |  | << Project task / activity
1.2 | 100% | Complete Project Management Plan | PM, Team | 2021-05-24 | 2021-07-18 | 55 day | 40 hours | 1.1 | << Project task / activity
1.3 | 100% | Set up Monitoring and Controlling processes | PM, Team | 2021-05-24 | 2021-07-18 | 55 day | 40 hours | 1.1 | << Project task / activity
1.4 | 100% | Management Activities Completed | PM, Team | 2021-07-18 | 2021-07-18 | - | - | - | << Milestone Task - no duration or work hours
2 |  | Initiation/Planning | [6 empty] | << Summary task
2.1 | 50% | Conduct Feasibility Study | PM, Team | 2021-06-07 | 2021-06-13 | 7 days | 4 hours | 1.1 | << Project task / activity
2.2 | 50% | Complete Business case | PM, Team | 2021-06-07 | 2021-06-13 | 7 days | 4 hours | 1.1 | << Project task / activity
2.3 | 50% | Complete Project Planning | PM, Team | 2021-05-31 | 2021-07-18 | 48 days | 40 hours | 1.1 | << Project task / activity
2.4 | 50% | Initiation/Planning Activities Completed | PM, Team | 2021-07-18 | 2021-07-18 | - | - | - | << Milestone Task - no duration or work hours
3 |  | Requirements Analysis
3.1 |  | Complete Requirements Gathering | Business Analyst | 2021-07-18 | 2021-07-30 | 15 days |  | 2.4
3.2 |  | Requirements Analysis Completed | Business Analyst | 2021-07-30 | 2021-07-30 | - | - | -
4 |  | Design
4.1 |  | Hold design workshops | Architect | 2021-07-30 | 2021-08-15 | 15 days | 40 hours | 3.2