## Log
RISK LOG
PROJECT TITLE: PMI CONFERENCE | [5 empty] | PROJECT MANAGER: ANUOLUWAPO BELLO | [7 empty] | DATE CREATED: 01/31/2024
IDENTIFY STAGE |  |  |  |  | ANALYZE STAGE |  |  |  | PLAN STAGE |  |  |  | ACTION STAGE
[6 empty] | RISK EVALUATION |  |  |  |  | PLANNED DATES |  | RISK MANAGEMENT PROCESS |  | RISK CLOSURE
| ID | Risk Originator | Short Description of Risk | Full Description of Risk | Risk Category | Likelihood | Impact | Proximity | Risk Management Plan | Owner | Target Completion | Next Review | Risk Status | Date | Status | Date
| 1 | Anuoluwapo Bello | Low attendance | The number of attendees registered for the conference falls below expectations, impacting revenue and potentially leading to financial losses. | Financial | High | High | Short | Develop contingency plans for lower attendance, including reduced costs for catering, venue, and other services. Diversify marketing efforts to reach a wider audience. | Sandra | 1931-03-01 | 2014-04-01 | Open | 2023-10-26 | Identified | 2023-10-26
| 2 | Anuoluwapo Bello | Speaker cancellation | A key speaker cancels their participation at the last minute, potentially impacting the value of the conference for attendees. | Quality | Medium | High | Short | Identify backup speakers for each topic and establish clear cancellation policies with speakers. Secure contracts with speakers upfront. | Anuoluwapo Bello | 1930-04-01 | 2012-05-01 | Open | 2023-10-26 | Identified | 2023-10-26
| 3 | Anuoluwapo Bello | Venue availability conflict | The contracted venue becomes unavailable due to unforeseen circumstances, requiring a last-minute change and potentially impacting logistics and costs. | Schedule | Medium | High | Short | Negotiate a flexible contract with the venue that allows for potential changes. Have backup venue options identified and readily available. | Queen Esther | 2028-02-01 | 2010-03-01 | Open | 2023-10-26 | Identified | 2023-10-26
| 4 | Anuoluwapo Bello | Website development delays | The development of the event website encounters delays, impacting marketing efforts and attendee registration. | Communication | Medium | Medium | Medium | Monitor website development progress closely and communicate any delays to stakeholders proactively. Establish clear deadlines and milestones for the website development process. | Christiana | 1930-04-01 | 2012-05-01 | Open | 2023-10-26 | Identified | 2023-10-26
| 5 | Anuoluwapo Bello | COVID-19 restrictions | The COVID-19 pandemic leads to restrictions on gatherings, potentially forcing the cancellation or postponement of the conference. | External | High | High | Short | Develop contingency plans for various scenarios, including virtual or hybrid event formats. Monitor COVID-19 updates closely and communicate with stakeholders proactively. | Mercy | Ongoing | Weekly | Open | 2023-10-26 | Identified | 2023-10-26

## Template Help
Overview / grading requirements:
An essential tool in any project management methodology is the risk log or risk register.
This provides a means of recording the identified risks, the analysis of their severity and the necessary management actions to be taken.
At a minimum, each risk filed into a risk register should contain a description of the risk, the impact to the business if the risk should occur (e.g. costs), the probability of its occurrence, the risk owner(s), how it ranks overall relative to all other risks, and the risk response.
Helpful Links:
https://projectmanagementacademy.net/resources/blog/risk-register-in-project-management/
https://www.youtube.com/watch?v=vkEPGFVVwfM
Example: