## Register
St. LOUIS PMI CONFERENCE
PROJECT NAME: ANUOLUWAPO B BELLO | [7 empty] | START DATE: 01/01/2024
S/N | Name of Stakeholder | Title/Position | Role | Department/Company | Contact Information | Type of Communication | Wants/Needs/Expectations/Concerns | Power | Interest
1 | Pam Meister | Executive Sponsor | Oversight and strategic direction | PMI St. Louis Chapter | Email: pam.meister@pmistlouis.org | Email, Meetings | Ensure project aligns with PMI's strategic goals, successful conference outcome | H | H
2 | Anuoluwapo Blessing Bello | Project Manager | Overall project management | PMI St. Louis Chapter | Email: anu.bello@pmistlouis.org | Email, Phone, Meetings | Successful execution, adherence to budget and timelines, stakeholder satisfaction | H | H
3 | Queen Esther | Logistics Lead | Venue, catering, and vendor coordination | PMI St. Louis Chapter | Email: queen.esther@pmistlouis.org | Email, Phone | Smooth operation of event logistics, vendor satisfaction, budget management | M | H
4 | Agnes Dell | Program Lead | Speaker and session coordination | PMI St. Louis Chapter | Email: agnes.dell@pmistlouis.org | Email, Phone | High-quality, engaging program content, speaker satisfaction, attendee engagement | M | H
5 | Robinson | Marketing & Sponsorship Lead | Marketing, promotions, sponsorships | PMI St. Louis Chapter | Email: robinson@pmistlouis.org | Email, Social Media | Effective marketing, sponsor acquisition and satisfaction, meeting registration targets | M | H
6 | Sandra | Finance Lead | Budget management and reporting | PMI St. Louis Chapter | Email: sandra@pmistlouis.org | Email, Phone | Budget adherence, financial reporting accuracy, cost savings | M | M
7 | Christiana | Technology Lead | Website and AV support | PMI St. Louis Chapter | Email: christiana@pmistlouis.org | Email, Phone | Reliable technology infrastructure, user-friendly registration system, minimal technical issues | M | H
8 | Victoria | Volunteer Coordinator | Volunteer recruitment and management | PMI St. Louis Chapter | Email: victoria@pmistlouis.org | Email, Phone | Effective volunteer engagement, adequate staffing for all events, volunteer satisfaction | L | M
9 | Evelyn | Social Media Manager | Online promotion and engagement | PMI St. Louis Chapter | Email: evelyn@pmistlouis.org | Social Media | Increased online visibility, attendee engagement, positive social media buzz | L | M
10 | Angel | Design and Branding Lead | Branding, marketing materials, signage | PMI St. Louis Chapter | Email: angel@pmistlouis.org | Email, Phone | Cohesive event branding, high-quality materials, brand visibility | L | M
11 | Isreal | Speaker Liaison | Speaker communication and arrangements | PMI St. Louis Chapter | Email: isreal@pmistlouis.org | Email, Phone | Speaker satisfaction, timely communication, logistical support | L | M
12 | Mercy | Risk Management Lead | Risk identification and mitigation | PMI St. Louis Chapter | Email: mercy@pmistlouis.org | Email, Meetings | Minimized risks, preparedness for unforeseen issues, stakeholder confidence | M | M

## Template Help
Overview / grading requirements:
A stakeholder register is a document that describes who (individual or group) is affected by a project, and their effect and impact on the project.
A stakeholder register is ideally completed early in the project to ensure proper engagement of stakeholders.
The purpose of the stakeholder register is to document who is impacted by the project/program, and their influence and impact on the project/program.
The stakeholder register is a living document, which serves the project manager and team for the life the project. It is the index of all project stakeholders and their essential attributes.
Helpful Links:
https://projectriskcoach.com/how-to-develop-a-stakeholder-register/
Example: